## Лист1
Task | Estimated time | Actual time
Texture creating
Create bonus pot textures | 2:00 | 2:17 | 12:40 | 11:40 | +1:19
Create cat textures | 2:00 | 1:19
Create explosive pot textures | 2:00 | 2:27
Create player textures | 3:00 | 2:38
Create gran gran textures | 5:00 | 3:40
Remake background atlas | 0:40 | 0:38
Gran gran render system
Gran entity | 0:10 | 0:05 | 1:00 | 0:47
Gran (state) component | 0:10 | 0:02
Gran render system | 0:40 | 0:40
Problem w/ rendering pots before/after the player
Order component | 0:10 | 0:04 | 1:00 | 0:26
Order system | 0:40 | 0:11
Divide pots render system | 0:10 | 0:11
Player render system
Player render system | 2:00 | 2:55 | 2:00 | 2:55
Shadows logic
Nothing | ? | 1:03 | 1:00 | 1:23
Actual making | 0:30 | 0:20
Bonuses
Golden bonus system | 0:20 |  | 1:40 | 1:09
Armor bonus system | 0:20 | 0:03
Heart bonus system | 0:20 | 0:02
Speed bonus system | 0:20 | 0:20
Time deceleration bonus system | 1:00
Bonus picking/removing | 0:20 | 0:26
Bonus render system | 0:20 | 0:18
Score system
Score system | 0:30 | 0:21 | 0:30 | 0:21
HUD system
Create HUD textures | 1:00 | 0:16 | 2:30 | 1:38
HUD system | 1:30 | 1:22
Game over logic
Death textures | 2:00 |  | 2:20
Game over logic | 0:20 | 0:20
UI Skin
Button texture | 1:00 | 0:38 | 6:20 | 4:44
Inactive button texture | 0:20 | 0:10
Loading screen textures | 1:30 | 2:39
Menu background texture | 1:00 | 0:23
Checkbox texture | 0:30 | 0:06
Dialog window texture | 1:00 | 0:07
Pack textures | 1:00 | 0:41
Screens
Menu screen | 2:00 | 0:57 | 5:45 | 3:16
Play screen | 0:45 | 0:35
Levels screen | 2:00 | 1:07
Options screen | 1:00 | 0:37
Options
GameConfigs class | 0:45 | 0:07 | 3:15
Research about account binding | 1:00 | 1:00
Account binding logic | 1:30
Windows
Locked function window | 0:30 | 0:38 | 1:30 | 2:11
Death window | 0:30 | 1:03
Victory window | 0:30 | 0:30
Sounds
Fixing bug with loading sounds | 1:30 |  | 7:00
Research for music and sounds | 2:00
Music play logic | 1:00
Sounds logic | 2:00
Music on/off in options screen | 0:30
Ads logic
Research | 1:30 |  | 2:30
Ads logic build in | 1:00